## Bug Reprt csv
BUG ID | Module | Severity | Priority | Title | Description | Steps_to_Reproduce | Expected_Result | Actual_Result | Status
Bug_ID | Module | Severity | Priority | Title | Description | Steps_to_Reproduce | Expected_Result | Actual_Result | Status
BUG001 | Login | Low | Low | Missing Remember Me checkbox | Login page doesn't have Remember Me checkbox | 1. Go to login page 2. Look for Remember Me option | Remember Me checkbox should be present | No Remember Me option found | Open
BUG002 | Cart | Medium | Medium | No empty cart message | Empty cart shows blank page | 1. Login 2. Click cart without adding items | Show Your cart is empty message | Cart page is blank | Open
BUG003 | Products | High | High | Sorting price low to high incorrect | Items not sorted correctly by price | 1. Login 2. Select Price (low to high) | Items from lowest to highest price | $49.99 item appears before $29.99 item | In Progress
BUG004 | UI | Medium | Low | Password shows plain text | Password field doesn't mask characters | 1. Go to login page 2. Type in password field | Characters appear as bullets | Characters appear as plain text | Fixed
BUG005 | Checkout | High | High | Tax calculation incorrect | Tax amount wrong for bulk orders | 1. Add 6 items 2. Go to checkout 3. Check tax | Tax should be 8% of total | Tax is less than 8% | Assigned

## Sheet1
Bug_ID,Module,Severity,Priority,Title,Description,Steps_to_Reproduce,Expected_Result,Actual_Result,Status
BUG001,Login,Low,Low,Missing Remember Me checkbox,Login page doesn't have Remember Me checkbox,"1. Go to login page\n2. Look for Remember Me option",Remember Me checkbox should be present,No Remember Me option found,Open
BUG002,Cart,Medium,Medium,No empty cart message,Empty cart shows blank page,"1. Login\n2. Click cart without adding items",Show "Your cart is empty" message,Cart page is blank,Open
BUG003,Products,High,High,Sorting price low to high incorrect,Items not sorted correctly by price,"1. Login\n2. Select Price (low to high)",Items from lowest to highest price,$49.99 item appears before $29.99 item,In Progress
BUG004,UI,Medium,Low,Password shows plain text,Password field doesn't mask characters,"1. Go to login page\n2. Type in password field",Characters appear as bullets,Characters appear as plain text,Open
BUG005,Checkout,High,High,Tax calculation incorrect,Tax amount wrong for bulk orders,"1. Add 6 items\n2. Go to checkout\n3. Check tax",Tax should be 8% of total,Tax is less than 8%,Assigned